## Template Retrospective
Sprint Retrospective | Iteration | 1
Project
Group | 90
For this sprint, we did not distinguish between user stories and tasks. This is because we did not have the system requirements yet and also since we did not have a good idea how libgdx is structured/works, or how exactly to make the game and split it up into very specific tasks. We just made a small product backlog on the gitlab issueboard, ordered on priority and took the most important ones. Although we think this was fine for the first sprint, for the next sprint we will split up user stories in smaller tasks, as described in the adjustments
User Story/Task |  | Task Assigned to | Estimated Effort (in hours) | Actual Effort | Done | Notes
Agree upon first libraries to use |  | Everyone | 1 | 1 | Yes
Set up libgdx |  | Victor, Maikel | 2 | 5 | Yes
Custom CI/CD |  | Victor | 3 | 3 | Yes
System requirements |  | Eduard, Tim | 5 | 5 | Yes
Implement ball physics |  | Maikel | 8 | 7 | As good as | Not fully merged since needs to be reviewed
Let the user interact with game elements |  | Jesse, Tim | 8 | 2 | No | Not possible since game elements not displayed/created yet
, and needed to spend much time on assignment 1
Show game elements |  | Jesse (,Victor, Eduard) | 5 | 7 | No | Only walls done, took a long time to understand and learn libgdx
Main Problems Encountered
Problem 1 | Unfinished tasks
Description | Too many tasks, the assignment and project organization took a lot of time, but still we can't forget really coding the game.
Reaction | More focus/time on coding needs to be spend. Everyone should spend more time in general and we decided to have 'weekly coding meeting' on Tuesday so everyone works on the project
Problem 2 | Large tasks
Description | Some tasks were quite large/did not have clear definition of done
Reaction | Although it was part of a conscious choice as explained above, for the next sprint we should have smaller tasks, with a clear definition of done. We should first pick some user stories of the product backlog, then split them up into smaller tasks and finally divide him. Something which will probably make this easier is first doing the planning on paper/in document and only then transform it to issues. This way we will have a better overview of the whole pictures. To display the user stories on gitlab, we can use labels/epics.
Problem 3 | Last-minute merges
Description | In the last few hours before the deadline we had to do a lot of merges to have some new code for the assignment release
Reaction | Next time create and handle merge requests a lot earlier. When someone has some small feature working, he should immediately make a merge request and say this in the group so 2 people can reveiw it. Retrospective is okay to do on Friday afternoon, but if a lot of problems/merges to be done it might be an idea to meet in the Thursday lab instead of just Friday afternoon
Adjustments for next Sprint Plan
Description
Task 1 | Spend more time on coding and have 'weekly coding meeting' on Tuesday
Task 2 | Make smaller tasks, first make sprint planning on paper/document, use labels/epics for user stories on gitlab
Task 3 | Create and handle merge request way earlier than last day, possibly meet in Thursday lab
Reflection: last week adjustments |  | NOT APPLICABLE, FIRST SPRINT SO NO ADJUSTMENTS FROM LAST WEEK