## Template Retrospective
Sprint Retrospective | Iteration | 2
Project
Group | 90
User Story (Epic) | Task | Task Assigned to | Estimated Effort (in hours per person) | Actual Effort (in hours per person) | Done | Notes
| Finish assignment 2 | Tim | 2 | 3 | Yes
Login | Implement user authentication | Victor | 5 | 5 | Yes
Login | Connect to database for authentication | Eduard | 3 | 3 | Yes
Postgame | Store score to database | Eduard | 1 | 1 | Yes
Postgame | Get leaderboard from database | Eduard | 2 | 1 | Yes
Login | Connect to server for authentication | Victor | 3 | 4 | Yes
Game rules | Allow the user to pot the ball into a pocket | Maikel | 2 | 5 | Yes
Shoot Ball | Implement ball collisions | Maikel | 2 | 2 | Yes
Login | Implement login screen | Jesse | 2 | 2 | Yes
Shoot Ball | Allow the user to rotate the cue | Tim | 3 | 2 | Yes
Shoot Ball | Allow the user to drag the cue for power | Tim | 2 | 2 | Yes
Setup game | Show pool table with walls and pockets | Jesse | 5 | 7 | Yes
Login | Display authentication errors | Victor/Jesse | 1 | 1 | Yes
Shoot Ball | Apply impulse on ball when cue is released | Tim | 1 | 1 | Yes
Setup game | Show initial state of the balls | Maikel | 5 | 7 | Yes
Main menu | Show main menu with "Play a Game" | Eduard | 2 | 2 | Yes
Because nearly everything we planned in was for the protoype (which needed to be done 1 week after the start of the sprint), halfway the sprint we only had 2/3 tasks left.
As the lecturer advised us, we did a mini-sprint planning to give everyone a few tasks for the rest of the sprint. We tried picking tasks with the most priority but the main thing we needed to think about is what we could and could not do in parallel (e.g. we couldn't implement the rules when we didnt have the classes to store the match state yet). Also, nothing really had huge importance since we already implemented everything needed for the prototype.
These are the tasks we worked on during the 2nd part of the sprint:
Game rules | Create match state and refactor Matchscreen | Tim | 8 | 4 | No | No, needs a lot of refactoring and
needed to wait for some other
tasks (like scoring)
Setup game | Use sprite for cue | Maikel | 3 | 4 | Yes
Postgame | Show leaderboard | Victor | 5 | 2 | No | Did not have enought time for this
Signup | Save new user to database | Victor, Eduard | 3 | 1 | Yes
Signup | Implement Sign-up screen | Jesse | 1 | 1 | Yes
Main menu | Extend main menu with "Leaderboard" and "Sound" button | Eduard | 1 | 1 | Yes
UX | Implement sound effects | Jesse | 3 | 1 | No | Needed to wait for potting to be
done, after that did not have
enough time left
Main menu | Extend main menu with "Settings" and "Logout" button | Eduard | 1 | 1 | Yes
Signup | Confirm password when signing up | Jesse, Victor | 1 | <1 | Yes | Just 1 if statement + extra test field ;)
Main Problems Encountered
Problem 1 | Lost track of time spent
Description | Because of the midterms inbetween and working in multiple stages for some tasks we did not know how long we exaclty worked on it
Reaction | Write down time spent somewhere, ideally under gitlab issue, but just for yourself is also okay, as long as we know it when doing the retrospective
Problem 2 | Sloppy upload' of assignment
Description | The assignment accidentally contained 2 of the same sequence diagrams, and the link to the whole class diagram picture was a bit outdated compared to the (partial) class diagrams in the pdf (just some small things). We should have checked this better.
Reaction | Before releasing the assignment, EVERYONE should double-check the assignment
Adjustments for next Sprint Plan
Description
Task 1 | Write down time spent during sprint
Task 2 | Double check assignment before handing in
Reflection: last week adjustments
| Description | Reflection
Task 1 | Spend more time on coding and have 'weekly coding meeting' on Tuesday | Did it, went really well
Task 2 | Make smaller tasks, first make sprint planning on paper/document, use labels/epics for user stories on gitlab | Achieved this. Made small tasks based on system requirements and used epics for grouping.
Didnt do it on paper in the end, with the sysrequirements & epics is was clear and easy enough
Task 3 | Create and handle merge request way earlier than last day, possibly meet in Thursday lab | First week was still a bit stressful because prototype was due in 1 week, but really improved in this and had to do a lot less last moment