## Template Retrospective
Sprint Retrospective | Iteration | 3
Project
Group | 90
User Story | Task | Task Assigned to | Estimated Effort (in hours per person) | Actual Effort (in hours per person) | Done | Notes
Game rules | Create match state and refactor Matchscreen | Tim | 5 | 5 | Yes
- | Do design patterns & software architecture tasks for assignment 3 | Tim, Eddie | 3 | 5 | Yes
Game rules | Implement turns | Eddie | 3 | 4 | Yes
Game rules | Implement fouls | Eddie | 3 | 4 | Yes
Postgame | Show leaderboard | Victor | 5 | 5 | Yes
Postgame | Ask user to save his score | Jesse | 2 | 2 | Yes
Postgame | Show Win/Lose message | Jesse | 2 | 2 | Yes
Game rules | Assign ball type to players | Maikel | 3 | 3 | Yes
- | Implement mutation testing | Victor | 8 | 3 | No | Other things had more priority
UX | Show extra elements during a match | Jesse | 5 | 1 | No | Didnt have enough time because of other tasks,
especially sounds took more time than expected
Game rules | End game when black ball | Maikel -> Tim | 5 | 5 | Yes | In the end Tim did this, because it matched better with his other tasks.
| is potted(win/lose) |  |  |  |  | Maikel and Tim swapped this one and 'Show power meter of hit'
UX | Implement sound effects | Jesse | 3 | 7 | Yes
Game rules | Time limit per turn | Eddie | 2 | 0 | No | No time because of busy schedule and assignment
Menu | Implement in-game menu | Eddie | 2 | 0 | No | No time because of busy schedule and assignment
Game rules | Allow user to place the white ball | Maikel | 5 | 10 | Yes | Not merged yet
| Show power meter of hit | Tim -> Maikel | 3 | 0 | No | Maikel and Tim swapped this one and 'End game when black ball is potted'
, because it turned out to match better with their other tasks.
Unfortunately, Maikel did not have enough time to work on this
Login | Logout button |  | 1 | 0.5 | Yes | We didn't plan this one in, but it was really easy to do (<10 lines of code)
Main Problems Encountered
Problem 1 | Merges to master
Description | We accidentally merged a feature branch to the master branch 2 times. However, we don't know if this is our own fault, because we remembered checking this and selecting dev when creating the request. Gitlab was down for a short time, and it could be it resetted/didnt save this setting. However, of course it is still our own fault. We fixed it by reverting the merge and creating a new merge requests for dev. Even though 1 was only 2 lines of code, we just wanted to adhere the pull-based development model, as we did during the whole project
Reaction | Check the target branch when creating the merge requests, reviewing one of others and just before merging. We probably won't have a lot of extra merges for this project, but this is definitely something to remember for future projects. Also if we were the owner of the repo we could have made dev the default branch.
Problem 2 | Little practice for presentation
Description | We started on Thursday with dividing the tasks and defining the structure. Then everyone did his own part, practised and time it. In the end our total presentation was 19,5 minutes, which is actualy perfect (required = 20 +- 1 min.). However, because we didn't practice that much and not together at all, the transitions were a bit weird and the practice presentation was not as good as it could have been.
Reaction | Practice more for the final presentation, and also a few times together. We already agreed upon 2 times to practice, and will probably add more depending on how it went.
Adjustments for next Sprint Plan
Description
Task 1 | Triple-check target branch of merge requests (see problem reaction for more comprehensive description)
Task 2 | Practice more for final presenation, together (see problem reaction for more comprehensive description)
Reflection: last week adjustments
| Description | Reflection
Task 1 | Write down time spent during sprint | Some people did it on gitlab, some did this for themselves on paper. Worked well, everyone remebered how long they spent
Task 2 | Double check assignment before handing in | We triple-checked the assignment, even found some mistakes, but finally uploaded the final version.
There shouldn't be mistakes in there (fingers crossed ;)